## 表紙
TE.035結合テスト仕様書/TE.040結合テストの実施と結果
株式会社伊藤園
基幹システムバージョンアップ
XXCFO：AP請求書明細付加情報更新処理抽出_BI Publisher
作成者: | SCSK 藤原祐介
作成日: | 2022-12-12
最終更新日: | 2023-11-07
文書管理番号: | T_TE035__CFO_007_A04
版: | Issue1.1
CONFIDENTIAL 株式会社伊藤園／SCSK株式会社
Copyright © 2022, SCSK Corporation. All rights reserved.

## 文書管理
文書管理
変更記録
| 日付 | 作成者 | 版 | 変更内容
| 2022-12-12 | SCSK 藤原祐介 | Draft1.0A | 新規作成
| 2023-02-08 | SCSK 二村悠香 | Issue1.0 | Issue化
| 2023-11-07 | SCSK 劉勇 | Issue1.1 | E_本稼動_19496対応

## テスト・シナリオ一覧
テスト・シナリオ一覧
以下に定義するテスト・シナリオに従って結合テストを実施します。
関連する結合テスト・シナリオは以下の通りです。
なし。
| テスト・シナリオ番号 | シナリオ概要
| シナリオ1 | ERP登録データ更新
| シナリオ2 | 抽出対象データなし時のデータ更新
| シナリオ3 | 運用時の想定最大件数のデータ更新
| シナリオ4 | 異常終了後の再実行
| シナリオ5 | ERP登録データ更新(E_本稼動_19496対応)
| シナリオ6 | 抽出対象データなし時のデータ更新(E_本稼動_19496対応)

## テスト仕様_データ・プロファイル
データ・プロファイル
各テスト・シナリオでは、以下に定義するデータを用い、テストを実施します。
テスト・シナリオ1
以下のデータを用いてテストを実施します。
| 表／ビュー名 | データ詳細
| AP_INVOICES_ALL AP_INVOICE_LINES_ALL | 「別紙(テスト・シナリオ1)」シートのデータパターンでERPCloudにて登録する。
テスト・シナリオ2
以下のデータを用いてテストを実施します。
| 表／ビュー名 | データ詳細
| AP_INVOICES_ALL AP_INVOICE_LINES_ALL | 更新対象のデータなし。（他シナリオで更新対象のデータは承認済みとし、対象外にする。）
テスト・シナリオ3
以下のデータを用いてテストを実施します。
| 表／ビュー名 | データ詳細
| AP_INVOICES_ALL AP_INVOICE_LINES_ALL | 購買オーダーの受入を実施し、請求書データを運用時の最大想定件数（345件程度）登録する。
テスト・シナリオ4
以下のデータを用いてテストを実施します。
| 表／ビュー名 | データ詳細
| AP_INVOICES_ALL AP_INVOICE_LINES_ALL | 購買オーダーの受入から請求書データを登録する。
テスト・シナリオ5
テスト・シナリオ1のデータを用いてテストを実施します。
テスト・シナリオ6
テスト・シナリオ2のデータを用いてテストを実施します。
ノート: ここではテストデータを記載します。テスト・シナリオ毎に、「テスト・ステップ」節で
記載したカラム名、及び、表／ビュー名をデータの内容を記載して下さい。
ノート: テストする機能が必要とするシード（事前設定）・データが記載対象です。
ノート: シード・データには、プロファイル・オプションも含みます。
ノート: 画面テスト時の入力値、およびコンカレント、共通関数のテスト時の入力パラメータは、
前項「テスト・ステップ」に記載して下さい。
ノート: 「表／ビュー名」には、シード・データが格納されている表・ビュー名を記載して下さい。
ノート: プロファイル・オプション値を設定しておく場合は、「表／ビュー名」欄に記載して下さい。
ノート: 「データ詳細」には、シード・データとして登録するデータの内容を文章で記載します。
また、処理の分岐の場合は、とりうる値にテスト・ステップ番号を併記し、全て記載して下さい。
例：2-1 △△区分＝'A' 2-2 △△区分＝'B'
ノート: また、複数のテスト・ステップで１つのシード・データが使用可能です。
例：正常終了確認のテスト・ステップと、抽出OK確認のテスト・ステップ
ノート: 既に表に登録したデータがある場合、当該表からSQLでSELECTした結果を巻末の
「参考資料」に添付し、「データ詳細」には巻末を参照する旨を記載しても構いません。

## テスト仕様_テスト結果(テスト・シナリオ5)
テスト仕様(テスト・ステップ)／テスト結果
各テスト・シナリオは、以下のテスト・ステップで構成されます。
各テスト・ステップに沿って結合テストを実施した結果を以下に記載します。
テスト・シナリオ5
以下のステップに従いテストを実施します。
| ステップNo. | テスト内容 | テスト対象機能 | 予想結果 | 実際の結果 | 判定 | テスター | 実施日
| 5-1 | BIP実行より対象データが抽出され、AP請求書明細の税分類コード(DFF11)および伝票作成会社(DFF15)が更新され、正常終了することを確認 以下スクリプトで実行します。 python /uspg/jp1/zb/py/devoicuser/XXCCD015.py /XXCFO/,XXCFO007A04EJ "" "" /ic/api/integration/v1/flows/rest/XXCFO007A05_02/1.0/RestUpdateApInvoiceDetail_AdditionalInfo | CB_AP請求書明細付加情報BIP_01 | Pythonスクリプトが正常終了します。 | 左記の通り | OK | 劉 | 2023-11-10
| 5-2 | ESSジョブの実行結果を確認 | AP請求書明細付加情報更新処理抽出_BI Publisher | ESSジョブが正常終了し、ステータスが「成功」になります。 | 左記の通り | OK | 劉 | 2023-11-10
| 5-3 | ESSジョブで出力したレポートの確認 | AP請求書明細付加情報更新処理抽出_BI Publisher | 文字コードが以下であること。 ・UTF8 | 左記の通り | OK | 劉 | 2023-11-10
| 5-4 |  |  | 文字化けがないこと。 | 左記の通り | OK | 劉 | 2023-11-10
| 5-5 |  |  | 対象件数が出力されること。 | 左記の通り | OK | 劉 | 2023-11-10
| 5-6 | OIC統合の確認 | AP請求書明細付加情報更新処理連携_OIC統合 | OIC統合が正常終了すること。 | 左記の通り | OK | 劉 | 2023-11-10
| 5-7 | データ更新の確認 ※更新対象は「別紙(テスト・シナリオ1)」シート参照 | AP請求書明細付加情報更新処理連携_OIC統合 | AP請求書明細の税分類コード(DFF11)が更新されること。 | 左記の通り | OK | 劉 | 2023-11-10
| 5-8 |  |  | AP請求書明細の伝票作成会社(DFF15)が更新されこと。 ※データパターンは「テスト・シナリオ5_別紙」シートを参照 | 左記の通り | OK | 劉 | 2023-11-10
エビデンス
T_TE040_CFO_007_A04_AP請求書明細付加情報更新処理抽出_BI Publisher_エビデンス.xlsx
【TE.020作成時の注意点】
ノート: テスト・シナリオ毎のテスト・ステップを記載して下さい。コンカレント・プログラムの場合は各プロセスの内部処理、
画面の場合は各機能の内部処理で、結果が分岐しうる処理を網羅するようにして下さい。
ノート: 「テスト内容」には、テスト・ステップ毎のテスト内容を記載して下さい。また、記載の上の注意は、以下を参照して下さい。
・処理が分岐しうる条件を、カラム名単位で詳細に記載して下さい。その際、カラム名は、
検証のポイントとなるカラムを選択して記載して下さい。
例：○○フラグ＝'Y'によって抽出対象となる事を確認
・データ取得ロジック(SELECT文)を確認する場合、SELECTできないケースも記載して下さい。
・１データを複数のテスト・ステップで使用する場合、以下の例を参考に記載して下さい。
例：シナリオX-Xと同時検証
ノート: 「テスト対象機能」には、「MD.050機能拡張に当っての機能設計書」（または「MD.070 機能拡張にあたっての
技術設計書」）で定義される「機能番号」および「機能名」を記載して下さい。
ノート: 画面テストの際に画面から入力する値は、「テスト内容」欄に記載して下さい。
ノート: コンカレント、共通関数のテスト実施の際に使用するパラメータは、「テスト内容」欄に記載して下さい。
【TE.070作成時の注意点】
ノート: テスト結果表に単体テスト結果を記載する際には、次のガイドラインに従います。
1）予想結果: 成否判定が可能な予想される結果または出力を記載します。
例：○○フラグ＝'Y'により抽出対象となる、××IDが不一致のため更新対象外となる
2）実際の結果: 実際にテスト・ステップで定義された内容でテストを実施した際の、
予想結果に対応する実際の結果または出力を記載します。
3）判定: 予想結果と実際の結果を比較し、テストの成否を判定した結果を以下の3つの記号で記載します。
・○: テスト成功
・×: テスト失敗
・－: 対象外（前ステップでテストが失敗し、テストが実施できなかったような場合に使用します。）
4）テスター: テスト実施者名を記載します。
5）実施日: テスト実施日の年月日を記載します。
ノート: パフォーマンス・テスト用のテスト・シナリオの場合、「予想結果」、「実際の結果」に処理時間を記載して下さい。
ノート: 再テストの場合、行を挿入して再テスト結果を記載してください。
ノート: 他に添付するエビデンスなどがあれば
記述します。

## テスト・シナリオ5_別紙
伝票作成会社のデータパターン
| No. | 仕入先サイト.伝票作成会社(DFF11) | AP請求書ヘッダ.記帳日 | DRAFTING_COMPANY（伝票作成会社）
| 1 | (NULL) | 2024/04/30 | 001
| 2 | (NULL) | 2024/05/01 | 001
| 3 | 001 | 2024/04/30 | 001
| 4 | 001 | 2024/05/01 | 001
| 5 | 002 | 2024/04/30 | 001
| 6 | 002 | 2024/05/01 | 002

## テスト仕様_テスト結果(テスト・シナリオ6)
テスト仕様(テスト・ステップ)／テスト結果
各テスト・シナリオは、以下のテスト・ステップで構成されます。
各テスト・ステップに沿って結合テストを実施した結果を以下に記載します。
テスト・シナリオ6
以下のステップに従いテストを実施します。
| ステップNo. | テスト内容 | テスト対象機能 | 予想結果 | 実際の結果 | 判定 | テスター | 実施日
| 6-1 | BIP実行より抽出したデータが0件でも、正常終了することを確認 以下スクリプトで実行します。 python /uspg/jp1/zb/py/devoicuser/XXCCD015.py /XXCFO/,XXCFO007A04EJ "" "" /ic/api/integration/v1/flows/rest/XXCFO007A05_02/1.0/RestUpdateApInvoiceDetail_AdditionalInfo | CB_AP請求書明細付加情報BIP_01 | Pythonスクリプトが正常終了します。 | 左記の通り | OK | 劉 | 2023-11-10
| 6-2 | ESSジョブの実行結果を確認 | AP請求書明細付加情報更新処理抽出_BI Publisher | ESSジョブが正常終了し、ステータスが「成功」になります。 | 左記の通り | OK | 劉 | 2023-11-10
| 6-3 | ESSジョブで出力したレポートの確認 | AP請求書明細付加情報更新処理抽出_BI Publisher | 0バイトのファイルを出力します。 | 左記の通り | OK | 劉 | 2023-11-10
| 6-4 | OIC統合の確認 | AP請求書明細付加情報更新処理連携_OIC統合 | OIC統合が正常終了すること。 | 左記の通り | OK | 劉 | 2023-11-10
エビデンス
T_TE040_CFO_007_A04_AP請求書明細付加情報更新処理抽出_BI Publisher_エビデンス.xlsx
【TE.020作成時の注意点】
ノート: テスト・シナリオ毎のテスト・ステップを記載して下さい。コンカレント・プログラムの場合は各プロセスの内部処理、
画面の場合は各機能の内部処理で、結果が分岐しうる処理を網羅するようにして下さい。
ノート: 「テスト内容」には、テスト・ステップ毎のテスト内容を記載して下さい。また、記載の上の注意は、以下を参照して下さい。
・処理が分岐しうる条件を、カラム名単位で詳細に記載して下さい。その際、カラム名は、
検証のポイントとなるカラムを選択して記載して下さい。
例：○○フラグ＝'Y'によって抽出対象となる事を確認
・データ取得ロジック(SELECT文)を確認する場合、SELECTできないケースも記載して下さい。
・１データを複数のテスト・ステップで使用する場合、以下の例を参考に記載して下さい。
例：シナリオX-Xと同時検証
ノート: 「テスト対象機能」には、「MD.050機能拡張に当っての機能設計書」（または「MD.070 機能拡張にあたっての
技術設計書」）で定義される「機能番号」および「機能名」を記載して下さい。
ノート: 画面テストの際に画面から入力する値は、「テスト内容」欄に記載して下さい。
ノート: コンカレント、共通関数のテスト実施の際に使用するパラメータは、「テスト内容」欄に記載して下さい。
【TE.070作成時の注意点】
ノート: テスト結果表に単体テスト結果を記載する際には、次のガイドラインに従います。
1）予想結果: 成否判定が可能な予想される結果または出力を記載します。
例：○○フラグ＝'Y'により抽出対象となる、××IDが不一致のため更新対象外となる
2）実際の結果: 実際にテスト・ステップで定義された内容でテストを実施した際の、
予想結果に対応する実際の結果または出力を記載します。
3）判定: 予想結果と実際の結果を比較し、テストの成否を判定した結果を以下の3つの記号で記載します。
・○: テスト成功
・×: テスト失敗
・－: 対象外（前ステップでテストが失敗し、テストが実施できなかったような場合に使用します。）
4）テスター: テスト実施者名を記載します。
5）実施日: テスト実施日の年月日を記載します。
ノート: パフォーマンス・テスト用のテスト・シナリオの場合、「予想結果」、「実際の結果」に処理時間を記載して下さい。
ノート: 再テストの場合、行を挿入して再テスト結果を記載してください。
ノート: 他に添付するエビデンスなどがあれば
記述します。

## テスト仕様_テスト結果(テスト・シナリオ1)
テスト仕様(テスト・ステップ)／テスト結果
各テスト・シナリオは、以下のテスト・ステップで構成されます。
各テスト・ステップに沿って結合テストを実施した結果を以下に記載します。
テスト・シナリオ1
以下のステップに従いテストを実施します。
| ステップNo. | テスト内容 | テスト対象機能 | 予想結果 | 実際の結果 | 判定 | テスター | 実施日
| 1-1 | OIC起動（手動） | ERP登録データ更新 | Pythonスクリプトが正常終了します。 | Pythonスクリプトが正常終了したことを確認 | OK | 細沼 | 2022-12-16
| 1-2 | ESSジョブの実行結果を確認 | ERP登録データ更新 | ESSジョブが正常終了し、ステータスが「成功」になります。 | ESSジョブが正常終了し、ステータスが「成功」となることを確認 | OK | 藤原 | 2022-12-16
| 1-3-1 | ESSジョブで出力したレポートの確認 | ERP登録データ更新 | 文字コードが以下であること。 ・UTF8 | 文字コードがUTF-8であることを確認 | OK | 藤原 | 2022-12-16
| 1-3-2 |  | ERP登録データ更新 | 文字化けがないこと。 | 文字化けがないことを確認 | OK | 藤原 | 2022-12-16
| 1-3-3 |  | ERP登録データ更新 | 対象件数が出力されること。 | 対象件数が出力されることを確認 | OK | 藤原 | 2022-12-16
| 1-4-1 | データ更新の確認 ※更新対象は「別紙(テスト・シナリオ1)」シート参照 | ERP登録データ更新 | AP請求書明細のATTRIBUTE11が更新されます。 | AP請求書明細のATTRIBUTE11が更新されることを確認 | OK | 藤原 | 2022-12-16
| 1-4-2 |  | ERP登録データ更新 | 対象データ以外は更新されません。 | 対象データ以外は更新されないことを確認。 | OK | 藤原 | 2022-12-16
エビデンス
T_TE040_CFO_007_A04_AP請求書明細付加情報更新処理抽出_BI Publisher_エビデンス.xlsx
【TE.020作成時の注意点】
ノート: テスト・シナリオ毎のテスト・ステップを記載して下さい。コンカレント・プログラムの場合は各プロセスの内部処理、
画面の場合は各機能の内部処理で、結果が分岐しうる処理を網羅するようにして下さい。
ノート: 「テスト内容」には、テスト・ステップ毎のテスト内容を記載して下さい。また、記載の上の注意は、以下を参照して下さい。
・処理が分岐しうる条件を、カラム名単位で詳細に記載して下さい。その際、カラム名は、
検証のポイントとなるカラムを選択して記載して下さい。
例：○○フラグ＝'Y'によって抽出対象となる事を確認
・データ取得ロジック(SELECT文)を確認する場合、SELECTできないケースも記載して下さい。
・１データを複数のテスト・ステップで使用する場合、以下の例を参考に記載して下さい。
例：シナリオX-Xと同時検証
ノート: 「テスト対象機能」には、「MD.050機能拡張に当っての機能設計書」（または「MD.070 機能拡張にあたっての
技術設計書」）で定義される「機能番号」および「機能名」を記載して下さい。
ノート: 画面テストの際に画面から入力する値は、「テスト内容」欄に記載して下さい。
ノート: コンカレント、共通関数のテスト実施の際に使用するパラメータは、「テスト内容」欄に記載して下さい。
【TE.070作成時の注意点】
ノート: テスト結果表に単体テスト結果を記載する際には、次のガイドラインに従います。
1）予想結果: 成否判定が可能な予想される結果または出力を記載します。
例：○○フラグ＝'Y'により抽出対象となる、××IDが不一致のため更新対象外となる
2）実際の結果: 実際にテスト・ステップで定義された内容でテストを実施した際の、
予想結果に対応する実際の結果または出力を記載します。
3）判定: 予想結果と実際の結果を比較し、テストの成否を判定した結果を以下の3つの記号で記載します。
・○: テスト成功
・×: テスト失敗
・－: 対象外（前ステップでテストが失敗し、テストが実施できなかったような場合に使用します。）
4）テスター: テスト実施者名を記載します。
5）実施日: テスト実施日の年月日を記載します。
ノート: パフォーマンス・テスト用のテスト・シナリオの場合、「予想結果」、「実際の結果」に処理時間を記載して下さい。
ノート: 再テストの場合、行を挿入して再テスト結果を記載してください。
ノート: 他に添付するエビデンスなどがあれば
記述します。

## 別紙(テスト・シナリオ1)
ERP登録データ連更新テストパターン
No. | 請求書ソース | 検証ステータス | 税分類コード | 更新対象 | 備考
1 | PO受入 | NEVER_APPROVED | ITEM | ○
2 |  |  | TAX | ○
3 | PO返品 | NEVER_APPROVED | ITEM | ○
4 |  |  | TAX | ○
5 | PO受入 | APPROVED | ITEM | ×
6 |  |  | TAX | ×
7 | PO返品 | APPROVED | ITEM | ×
8 |  |  | TAX | ×
9 | ERPCloud手入力 | NEVER_APPROVED | ITEM | ×
10 |  |  | TAX | ×

## テスト仕様_テスト結果(テスト・シナリオ2)
テスト仕様(テスト・ステップ)／テスト結果
各テスト・シナリオは、以下のテスト・ステップで構成されます。
各テスト・ステップに沿って結合テストを実施した結果を以下に記載します。
テスト・シナリオ2
以下のステップに従いテストを実施します。
| ステップNo. | テスト内容 | テスト対象機能 | 予想結果 | 実際の結果 | 判定 | テスター | 実施日
| 2-1 | OIC起動（手動） | 抽出対象データなし時のデータ更新 | Pythonスクリプトが正常終了します。 | Pythonスクリプトが正常終了したことを確認 | OK | 細沼 | 2022-12-19
| 2-2 | ESSジョブの実行結果を確認 | 抽出対象データなし時のデータ更新 | ESSジョブが正常終了し、ステータスが「成功」になります。 | ESSジョブが正常終了し、ステータスが「成功」となることを確認 | OK | 藤原 | 2022-12-19
| 2-3 | ESSジョブで出力したレポートの確認 | 抽出対象データなし時のデータ更新 | 0バイトのファイルを出力します。 | 0バイトのファイルが出力されることを確認 | OK | 藤原 | 2022-12-19
| 2-4 | データ更新の確認 | ERP登録データ更新 | 請求書明細が更新されないこと。 | 請求書明細が更新されないことを確認 | OK | 藤原 | 2022-12-19
エビデンス
T_TE040_CFO_007_A04_AP請求書明細付加情報更新処理抽出_BI Publisher_エビデンス.xlsx
【TE.020作成時の注意点】
ノート: テスト・シナリオ毎のテスト・ステップを記載して下さい。コンカレント・プログラムの場合は各プロセスの内部処理、
画面の場合は各機能の内部処理で、結果が分岐しうる処理を網羅するようにして下さい。
ノート: 「テスト内容」には、テスト・ステップ毎のテスト内容を記載して下さい。また、記載の上の注意は、以下を参照して下さい。
・処理が分岐しうる条件を、カラム名単位で詳細に記載して下さい。その際、カラム名は、
検証のポイントとなるカラムを選択して記載して下さい。
例：○○フラグ＝'Y'によって抽出対象となる事を確認
・データ取得ロジック(SELECT文)を確認する場合、SELECTできないケースも記載して下さい。
・１データを複数のテスト・ステップで使用する場合、以下の例を参考に記載して下さい。
例：シナリオX-Xと同時検証
ノート: 「テスト対象機能」には、「MD.050機能拡張に当っての機能設計書」（または「MD.070 機能拡張にあたっての
技術設計書」）で定義される「機能番号」および「機能名」を記載して下さい。
ノート: 画面テストの際に画面から入力する値は、「テスト内容」欄に記載して下さい。
ノート: コンカレント、共通関数のテスト実施の際に使用するパラメータは、「テスト内容」欄に記載して下さい。
【TE.070作成時の注意点】
ノート: テスト結果表に単体テスト結果を記載する際には、次のガイドラインに従います。
1）予想結果: 成否判定が可能な予想される結果または出力を記載します。
例：○○フラグ＝'Y'により抽出対象となる、××IDが不一致のため更新対象外となる
2）実際の結果: 実際にテスト・ステップで定義された内容でテストを実施した際の、
予想結果に対応する実際の結果または出力を記載します。
3）判定: 予想結果と実際の結果を比較し、テストの成否を判定した結果を以下の3つの記号で記載します。
・○: テスト成功
・×: テスト失敗
・－: 対象外（前ステップでテストが失敗し、テストが実施できなかったような場合に使用します。）
4）テスター: テスト実施者名を記載します。
5）実施日: テスト実施日の年月日を記載します。
ノート: パフォーマンス・テスト用のテスト・シナリオの場合、「予想結果」、「実際の結果」に処理時間を記載して下さい。
ノート: 再テストの場合、行を挿入して再テスト結果を記載してください。
ノート: 他に添付するエビデンスなどがあれば
記述します。

## テスト仕様_テスト結果(テスト・シナリオ3)
テスト仕様(テスト・ステップ)／テスト結果
各テスト・シナリオは、以下のテスト・ステップで構成されます。
各テスト・ステップに沿って結合テストを実施した結果を以下に記載します。
テスト・シナリオ3
以下のステップに従いテストを実施します。
| ステップNo. | テスト内容 | テスト対象機能 | 予想結果 | 実際の結果 | 判定 | テスター | 実施日
| 3-1 | OIC起動（手動） | 運用時の想定最大件数のデータ更新 | Pythonスクリプトが正常終了します。 | Pythonスクリプトが正常終了したことを確認 | OK | 細沼 | 2022-12-16
| 3-2 | ESSジョブの実行結果を確認 | 運用時の想定最大件数のデータ更新 | ESSジョブが正常終了し、ステータスが「成功」になります。 | ESSジョブが正常終了し、ステータスが「成功」となることを確認 | OK | 藤原 | 2022-12-16
| 3-3 | ESSジョブで出力したレポートの確認 | 運用時の想定最大件数のデータ更新 | 対象件数が出力されること。 | 対象件数が出力されることを確認 | OK | 藤原 | 2022-12-16
| 3-4-1 | データ更新の確認 ※更新対象は「別紙(テスト・シナリオ1)」シート参照 | 運用時の想定最大件数のデータ更新 | AP請求書明細のATTRIBUTE11が更新されます。 | AP請求書明細のATTRIBUTE11が更新されることを確認 | OK | 藤原 | 2022-12-16
| 3-4-2 |  | 運用時の想定最大件数のデータ更新 | 対象データ以外は更新されません。 | 対象データ以外は更新されないことを確認。 | OK | 藤原 | 2022-12-16
エビデンス
T_TE040_CFO_007_A04_AP請求書明細付加情報更新処理抽出_BI Publisher_エビデンス.xlsx
【TE.020作成時の注意点】
ノート: テスト・シナリオ毎のテスト・ステップを記載して下さい。コンカレント・プログラムの場合は各プロセスの内部処理、
画面の場合は各機能の内部処理で、結果が分岐しうる処理を網羅するようにして下さい。
ノート: 「テスト内容」には、テスト・ステップ毎のテスト内容を記載して下さい。また、記載の上の注意は、以下を参照して下さい。
・処理が分岐しうる条件を、カラム名単位で詳細に記載して下さい。その際、カラム名は、
検証のポイントとなるカラムを選択して記載して下さい。
例：○○フラグ＝'Y'によって抽出対象となる事を確認
・データ取得ロジック(SELECT文)を確認する場合、SELECTできないケースも記載して下さい。
・１データを複数のテスト・ステップで使用する場合、以下の例を参考に記載して下さい。
例：シナリオX-Xと同時検証
ノート: 「テスト対象機能」には、「MD.050機能拡張に当っての機能設計書」（または「MD.070 機能拡張にあたっての
技術設計書」）で定義される「機能番号」および「機能名」を記載して下さい。
ノート: 画面テストの際に画面から入力する値は、「テスト内容」欄に記載して下さい。
ノート: コンカレント、共通関数のテスト実施の際に使用するパラメータは、「テスト内容」欄に記載して下さい。
【TE.070作成時の注意点】
ノート: テスト結果表に単体テスト結果を記載する際には、次のガイドラインに従います。
1）予想結果: 成否判定が可能な予想される結果または出力を記載します。
例：○○フラグ＝'Y'により抽出対象となる、××IDが不一致のため更新対象外となる
2）実際の結果: 実際にテスト・ステップで定義された内容でテストを実施した際の、
予想結果に対応する実際の結果または出力を記載します。
3）判定: 予想結果と実際の結果を比較し、テストの成否を判定した結果を以下の3つの記号で記載します。
・○: テスト成功
・×: テスト失敗
・－: 対象外（前ステップでテストが失敗し、テストが実施できなかったような場合に使用します。）
4）テスター: テスト実施者名を記載します。
5）実施日: テスト実施日の年月日を記載します。
ノート: パフォーマンス・テスト用のテスト・シナリオの場合、「予想結果」、「実際の結果」に処理時間を記載して下さい。
ノート: 再テストの場合、行を挿入して再テスト結果を記載してください。
ノート: 他に添付するエビデンスなどがあれば
記述します。

## テスト仕様_テスト結果(テスト・シナリオ4)
テスト仕様(テスト・ステップ)／テスト結果
各テスト・シナリオは、以下のテスト・ステップで構成されます。
各テスト・ステップに沿って結合テストを実施した結果を以下に記載します。
テスト・シナリオ4
以下のステップに従いテストを実施します。
| ステップNo. | テスト内容 | テスト対象機能 | 予想結果 | 実際の結果 | 判定 | テスター | 実施日
| 4-1-1 | ※PaaSのDBとERPCloudが接続できない状態にして実施する。 OIC起動（手動） | 異常終了 | Pythonスクリプトが異常終了します。 | Pythonスクリプトが異常終了したことを確認 | OK | 細沼 | 2022-12-19
| 4-1-2 | ESSジョブの実行結果を確認 | 異常終了 | ESSジョブは実行されません。 | ESSジョブが実行されていないことを確認 | OK | 藤原 | 2022-12-19
| 4-2-1 | ※PaaSのDBとERPCloudが接続可能な状態に戻す。 OIC起動（手動） | 異常終了後の再実行 | Pythonスクリプトが正常終了します。 | Pythonスクリプトが正常終了したことを確認 | OK | 細沼 | 2022-12-19
| 4-2-2 | ESSジョブの実行結果を確認 | 異常終了後の再実行 | ESSジョブが正常終了し、ステータスが「成功」になります。 | ESSジョブが正常終了し、ステータスが「成功」となることを確認 | OK | 藤原 | 2022-12-19
| 4-2-3 | ESSジョブで出力したレポートの確認 | 異常終了後の再実行 | 対象件数が出力されること。 | 対象件数が出力されることを確認 | OK | 藤原 | 2022-12-19
| 4-2-4 | データ更新の確認 ※更新対象は「別紙(テスト・シナリオ1)」シート参照 | 異常終了後の再実行 | AP請求書明細のATTRIBUTE11が更新されます。 | AP請求書明細のATTRIBUTE11が更新されることを確認 | OK | 藤原 | 2022-12-19
| 4-2-5 |  | 異常終了後の再実行 | 対象データ以外は更新されません。 | 対象データ以外は更新されないことを確認。 | OK | 藤原 | 2022-12-19
エビデンス
T_TE040_CFO_007_A04_AP請求書明細付加情報更新処理抽出_BI Publisher_エビデンス.xlsx
【TE.020作成時の注意点】
ノート: テスト・シナリオ毎のテスト・ステップを記載して下さい。コンカレント・プログラムの場合は各プロセスの内部処理、
画面の場合は各機能の内部処理で、結果が分岐しうる処理を網羅するようにして下さい。
ノート: 「テスト内容」には、テスト・ステップ毎のテスト内容を記載して下さい。また、記載の上の注意は、以下を参照して下さい。
・処理が分岐しうる条件を、カラム名単位で詳細に記載して下さい。その際、カラム名は、
検証のポイントとなるカラムを選択して記載して下さい。
例：○○フラグ＝'Y'によって抽出対象となる事を確認
・データ取得ロジック(SELECT文)を確認する場合、SELECTできないケースも記載して下さい。
・１データを複数のテスト・ステップで使用する場合、以下の例を参考に記載して下さい。
例：シナリオX-Xと同時検証
ノート: 「テスト対象機能」には、「MD.050機能拡張に当っての機能設計書」（または「MD.070 機能拡張にあたっての
技術設計書」）で定義される「機能番号」および「機能名」を記載して下さい。
ノート: 画面テストの際に画面から入力する値は、「テスト内容」欄に記載して下さい。
ノート: コンカレント、共通関数のテスト実施の際に使用するパラメータは、「テスト内容」欄に記載して下さい。
【TE.070作成時の注意点】
ノート: テスト結果表に単体テスト結果を記載する際には、次のガイドラインに従います。
1）予想結果: 成否判定が可能な予想される結果または出力を記載します。
例：○○フラグ＝'Y'により抽出対象となる、××IDが不一致のため更新対象外となる
2）実際の結果: 実際にテスト・ステップで定義された内容でテストを実施した際の、
予想結果に対応する実際の結果または出力を記載します。
3）判定: 予想結果と実際の結果を比較し、テストの成否を判定した結果を以下の3つの記号で記載します。
・○: テスト成功
・×: テスト失敗
・－: 対象外（前ステップでテストが失敗し、テストが実施できなかったような場合に使用します。）
4）テスター: テスト実施者名を記載します。
5）実施日: テスト実施日の年月日を記載します。
ノート: パフォーマンス・テスト用のテスト・シナリオの場合、「予想結果」、「実際の結果」に処理時間を記載して下さい。
ノート: 再テストの場合、行を挿入して再テスト結果を記載してください。
ノート: 他に添付するエビデンスなどがあれば
記述します。

## 不具合ログ
不具合ログ
以下に単体テスト時の不具合を記録します。
| 不具合ID | シナリオ・ | 不具合の説明 | 解決策 | 再テスト担当者 | 再テスト日付 | ステータス
ステップ

## 未完了の課題と完了済みの課題
この成果物の未完了の課題と完了済みの課題
未完了の課題
| ID | 課題 | 解決策 | 担当 | 目標日付 | 期限
完了済みの課題
| ID | 課題 | 解決策 | 担当 | 目標日付 | 期限

## AP_INVOICE_LINES_ALL
AP_INVOICE_LINES_ALL
AP_INVOICE_LINES_ALL contains records for invoice lines entered manually, generated automatically or imported from the Open Interface. An invoice can have one or more invoice lines. An invoice line can have one or more invoice distributions. An invoice line represents goods (direct or indirect materials), service(s), and/or associated tax/freight/miscellaneous charges invoiced from a supplier. An invoice line should contain all the attributes that are present on the physical or electronic invoice presented by the supplier. These attributes should suffice in specifying the charge/expense/asset information that makes up the invoice line. An invoice line can be of any of the following types: Item, Freight, Miscellaneous, Tax, Prepayment or Withholding Tax. Prepayment Lines are generated via prepayment application. Item type lines may represent a match to a purchase order or receipt, a price correction against an existing purchase order or receipt matched invoice line, a quantity correction against an existing purchase order or receipt matched invoice line, an invoice correction against an existing non-matched invoice line or a non-matched invoice line. Freight and Miscellaneous lines may represent a match to a Receipt or may be non-matched. Freight and Miscellaneous type lines may be allocated to Item type lines whenever they are not themselves matched to a receipt. Rules for allocation may be entered in the Allocations module. Allocations are stamped on the distributions for such a Freight or Miscellaneous type line. Lines may be generated automatically via any of the following methods: . Match to purchase order or receipt requested from the invoice header . Generation of freight automatically from the invoice header . Generation of Item line from Distribution Set requested from the invoice header . Generation of Freight/Miscellaneous from purchase order or receipt matching windows . Prepayment application Lines will also be created during import of Open Interface invoices. It is the distributions for a line, and not the line itself, that will carry the status relative to Validation, Encumbrance, and Accounting. Furthermore, it is the Distributions for a line that get transferred to Oracle Assets and/or processed by Oracle Projects. However, lines will contain an Approval status. A line may be discarded on its own or as part of cancellation of the invoice. A discarded line will have an amount of 0 and will be marked as discarded. During discarding of a line, appropriate distributions are generated to reverse the effect of any existing distributions for the line
Details
Schema: FUSION
Object owner: AP
Object type: TABLE
Tablespace: FUSION_TS_TX_DATA
Primary Key
Name | Columns
AP_INVOICE_LINES_ALL_PK | INVOICE_ID, LINE_NUMBER
Columns
Name | Datatype | Length | Precision | Not-null | Comments | Flexfield-mapping | Status
INVOICE_ID | NUMBER |  | 18 | Yes | Invoice line number associated with the event. |  | Active
LINE_NUMBER | NUMBER |  | 18 | Yes | Number of the invoice line. |  | Active
LINE_TYPE_LOOKUP_CODE | VARCHAR2 | 25 |  | Yes | Type of invoice line. Valid values from INVOICE LINE TYPE lookup codes. |  | Active
REQUESTER_ID | NUMBER |  | 18 |  | The name of the person who the requested items are intended for. |  | Active
DESCRIPTION | VARCHAR2 | 240 |  |  | Description of the invoice line. |  | Active
LINE_SOURCE | VARCHAR2 | 30 |  |  | Source of the invoice line. Validated against AP_LOOKUP_CODES.LOOKUP_CODE for LOOKUP_TYPE LINE SOURCE |  | Active
ORG_ID | NUMBER |  | 18 | Yes | Indicates the identifier of the business unit associated to the row. |  | Active
LINE_GROUP_NUMBER | NUMBER |  |  |  | Group number assigned to the line during the Open Interface Import process to be used for generation of allocation rules |  | Active
INVENTORY_ITEM_ID | NUMBER |  |  |  | Inventory item identifier. Validated against EGP_SYSTEM_ITEMS.INVENTORY_ITEM_ID |  | Active
ITEM_DESCRIPTION | VARCHAR2 | 240 |  |  | Description of the item in the invoice line. |  | Active
SERIAL_NUMBER | VARCHAR2 | 35 |  |  | Number indicating place in a series, used for identification. |  | Active
MANUFACTURER | VARCHAR2 | 30 |  |  | Manufacturer of an asset or item. |  | Active
MODEL_NUMBER | VARCHAR2 | 40 |  |  | Model number of the invoice line item. |  | Active
WARRANTY_NUMBER | VARCHAR2 | 15 |  |  | Warranty number of the item that is available for item lines. |  | Active
GENERATE_DISTS | VARCHAR2 | 1 |  |  | Flag indicating whether distributions for the invoice line should be generated dynamically whenever possible |  | Active
MATCH_TYPE | VARCHAR2 | 25 |  |  | Indicates the type of match if any. Validated against AP_LOOKUP_CODES with lookup type as INVOICE LINE MATCH TYPE |  | Active
DISTRIBUTION_SET_ID | NUMBER |  | 18 |  | Distribution set identifier to be used in the generation of distributions for a line |  | Active
ACCOUNT_SEGMENT | VARCHAR2 | 25 |  |  | Account segment value for overlay in generation of accounting flexfield during distribution generation |  | Active
BALANCING_SEGMENT | VARCHAR2 | 25 |  |  | Balancing segment value for overlay in generation of accounting flexfield during distribution generation |  | Active
COST_CENTER_SEGMENT | VARCHAR2 | 25 |  |  | Cost Center segment value for overlay in generation of accounting flexfield during distribution generation |  | Active
OVERLAY_DIST_CODE_CONCAT | VARCHAR2 | 250 |  |  | Concatenated segments for overlay in generation of accounting flexfield during distribution generation |  | Active
DEFAULT_DIST_CCID | NUMBER |  | 18 |  | Account to be used for automatic generation of a single distribution |  | Active
PRORATE_ACROSS_ALL_ITEMS | VARCHAR2 | 1 |  |  | A value of Y indicates that the Freight or Miscellaneous type line should be prorated across all Item type lines |  | Active
ACCOUNTING_DATE | DATE |  |  | Yes | Accounting date for invoice line. Used for defaulting to distributions |  | Active
PERIOD_NAME | VARCHAR2 | 15 |  |  | Accounting date for invoice line. Used for defaulting to distributions |  | Active
DEFERRED_ACCTG_FLAG | VARCHAR2 | 1 |  |  | Accounting date for invoice line. Used for defaulting to distributions |  | Active
DEF_ACCTG_START_DATE | DATE |  |  |  | The start date of the deferred expense period |  | Active
DEF_ACCTG_END_DATE | DATE |  |  |  | The end date of the deferred expense period |  | Active
DEF_ACCTG_NUMBER_OF_PERIODS | NUMBER |  |  |  | Number of periods to generate deferred expenses. Used in combination with PERIOD_TYPE. Alternative to END_DATE |  | Active
DEF_ACCTG_PERIOD_TYPE | VARCHAR2 | 30 |  |  | Period type used in combination with NUMBER_OF_PERIODS to generate deferred expenses. Validated against XLA_LOOKUPS with lookup type XLA_DEFERRED_PERIOD_TYPE |  | Active
SET_OF_BOOKS_ID | NUMBER |  | 18 | Yes | Ledger identifier of the invoice line. |  | Active
AMOUNT | NUMBER |  |  | Yes | Line amount in invoice currency |  | Active
BASE_AMOUNT | NUMBER |  |  |  | Line amount in functional currency |  | Active
ROUNDING_AMT | NUMBER |  |  |  | Amount corresponding to rounding amount included in BASE_AMOUNT if any |  | Active
QUANTITY_INVOICED | NUMBER |  |  |  | Quantity invoiced. Quantity of items for matched invoice lines, price corrections, quantity corrections or unmatched invoice lines |  | Active
UNIT_MEAS_LOOKUP_CODE | VARCHAR2 | 25 |  |  | Unit of measure for QUANTITY_INVOICED. Validated against INV_UNITS_OF_MEASURE.UNIT_OF_MEASURE |  | Active
UNIT_PRICE | NUMBER |  |  |  | Price charged per unit of a good or service. |  | Active
WFAPPROVAL_STATUS | VARCHAR2 | 30 |  | Yes | Indicates if an invoice line has been approved. |  | Active
USSGL_TRANSACTION_CODE | VARCHAR2 | 30 |  |  | USSGL Transaction Code for creating U.S. Standard General Ledger journal entries (Oracle Public Sector Payables). Validated against GL_USSGL_TRANSACTION_CODES.USSGL_TRANSACTION_CODE |  | Active
DISCARDED_FLAG | VARCHAR2 | 1 |  |  | A value of Y indicates that the line has been discarded. When a line is discarded all its distributions are reversed and the AMOUNT is set to 0 |  | Active
ORIGINAL_AMOUNT | NUMBER |  |  |  | Amount of the line before discarding of the line or cancellation of the invoice |  | Active
ORIGINAL_BASE_AMOUNT | NUMBER |  |  |  | Base amount of the line before discarding of the line or cancellation of the invoice |  | Active
ORIGINAL_ROUNDING_AMT | NUMBER |  |  |  | Rounding amount of the line before discarding of the line or cancellation of the invoice |  | Active
CANCELLED_FLAG | VARCHAR2 | 1 |  |  | Indicates if invoice line is canceled. |  | Active
INCOME_TAX_REGION | VARCHAR2 | 10 |  |  | Reporting region for invoice line for 1099 supplier. Defaults down to distributions |  | Active
TYPE_1099 | VARCHAR2 | 10 |  |  | Indicates the category of the withholding tax rates. |  | Active
STAT_AMOUNT | NUMBER |  |  |  | Amount associated with a distribution for measuring statistical quantities. Used only for transferring the information during Open Interface Import process |  | Active
PREPAY_INVOICE_ID | NUMBER |  | 18 |  | Invoice identifier for Prepayment invoice applied via current invoice line |  | Active
PREPAY_LINE_NUMBER | NUMBER |  |  |  | Line number for Prepayment line applied via current invoice line |  | Active
INVOICE_INCLUDES_PREPAY_FLAG | VARCHAR2 | 1 |  |  | Y indicates that prepayment is included in the invoice amount |  | Active
CORRECTED_INV_ID | NUMBER |  | 18 |  | Invoice identifier for invoice corrected via current line. For price, quantity, or invoice line corrections |  | Active
CORRECTED_LINE_NUMBER | NUMBER |  |  |  | Invoice line number for invoice line corrected via current line. For price, quantity, or invoice line corrections |  | Active
PO_HEADER_ID | NUMBER |  |  |  | A commercial document that is used to request a seller to supply a product or service in return for payment. |  | Active
PO_LINE_ID | NUMBER |  |  |  | A line identifier for the line record on a transaction. The Purchase Order Line describes an item or service, with a price and quantity ordered. |  | Active
PO_RELEASE_ID | NUMBER |  |  |  | Number of the purchase order release associated with the invoice correction |  | Active
PO_LINE_LOCATION_ID | NUMBER |  |  |  | Ship-to location for the purchase order schedule. |  | Active
PO_DISTRIBUTION_ID | NUMBER |  |  |  | Purchase order distribution line which indicates the accounting transactions for the goods or services. |  | Active
RCV_TRANSACTION_ID | NUMBER |  |  |  | Line on the shipment receipt. |  | Active
FINAL_MATCH_FLAG | VARCHAR2 | 1 |  |  | Indicates if an invoice is the last one being matched to a PO, so that the PO is no longer available for matching. |  | Active
ASSETS_TRACKING_FLAG | VARCHAR2 | 1 |  |  | Y indicates that the item should be treated as an asset |  | Active
ASSET_BOOK_TYPE_CODE | VARCHAR2 | 30 |  |  | Asset Book. Defaults to the distributions candidate for transfer to Oracle Assets |  | Active
ASSET_CATEGORY_ID | NUMBER |  | 18 |  | Asset Category. Defaults to the distributions candidate for transfer to Oracle Assets |  | Active
PROJECT_ID | NUMBER |  | 18 |  | Project identifier for project related invoice lines |  | Active
TASK_ID | NUMBER |  | 18 |  | Task identifier for project related invoice lines |  | Active
EXPENDITURE_TYPE | VARCHAR2 | 30 |  |  | Expenditure type for project related invoice lines |  | Active
EXPENDITURE_ITEM_DATE | DATE |  |  |  | Expenditure item date for project related Invoice Lines |  | Active
EXPENDITURE_ORGANIZATION_ID | NUMBER |  | 18 |  | Expenditure organization identifier for project related invoice lines |  | Active
PA_QUANTITY | NUMBER |  |  |  | Project item quantity for project related invoice lines |  | Active
PA_CC_AR_INVOICE_ID | NUMBER |  | 18 |  | For an intercompany invoice from Oracle Projects, this is the identifier of the corresponding receivable intercompany invoice in Oracle Receivables |  | Active
PA_CC_AR_INVOICE_LINE_NUM | NUMBER |  | 18 |  | For an intercompany invoice from Oracle Projects, this is the line number of the corresponding receivable intercompany invoice in Oracle Receivables |  | Active
PA_CC_PROCESSED_CODE | VARCHAR2 | 1 |  |  | The processing status of this invoice line by Oracle Projects in the receiver operating unit |  | Active
AWARD_ID | NUMBER |  | 18 |  | Reserved for use by Oracle Grants Management. Defaults to distributions |  | Active
AWT_GROUP_ID | NUMBER |  | 18 |  | Withholding tax group identifier |  | Active
REFERENCE_1 | VARCHAR2 | 30 |  |  | A reference to a record in another application |  | Active
REFERENCE_2 | VARCHAR2 | 30 |  |  | A reference to a record in another application |  | Active
RECEIPT_VERIFIED_FLAG | VARCHAR2 | 1 |  |  | Indicates whether receipts verified |  | Active
RECEIPT_REQUIRED_FLAG | VARCHAR2 | 1 |  |  | Indicates whether receipts required |  | Active
RECEIPT_MISSING_FLAG | VARCHAR2 | 1 |  |  | Indicates whether receipts missing |  | Active
JUSTIFICATION | VARCHAR2 | 240 |  |  | Reason, fact, circumstance, or explanation that justifies or defends. |  | Active
EXPENSE_GROUP | VARCHAR2 | 80 |  |  | Expense group associated with the invoice line. |  | Active
START_EXPENSE_DATE | DATE |  |  |  | Date when incurred expense started. Used for expense reports |  | Active
END_EXPENSE_DATE | DATE |  |  |  | Date when incurred expense ended. Used for expense reports |  | Active
RECEIPT_CURRENCY_CODE | VARCHAR2 | 15 |  |  | Currency code of receipt. Used for expense reports |  | Active
RECEIPT_CONVERSION_RATE | NUMBER |  |  |  | Exchange rate for currency of receipt. Used for expense reports |  | Active
RECEIPT_CURRENCY_AMOUNT | NUMBER |  |  |  | Amount in receipt currency. Used for expense reports |  | Active
DAILY_AMOUNT | NUMBER |  |  |  | Daily expense amount. Used for expense reports |  | Active
WEB_PARAMETER_ID | NUMBER |  |  |  | Self-Service Web Applications parameter identifier |  | Active
ADJUSTMENT_REASON | VARCHAR2 | 240 |  |  | Reason for adjustment on the invoice line. |  | Active
MERCHANT_DOCUMENT_NUMBER | VARCHAR2 | 80 |  |  | Third party document number. Used for expense reports |  | Active
MERCHANT_NAME | VARCHAR2 | 80 |  |  | Third party name. Used for expense reports |  | Active
MERCHANT_REFERENCE | VARCHAR2 | 240 |  |  | Third party reference. Used for expense reports |  | Active
MERCHANT_TAX_REG_NUMBER | VARCHAR2 | 80 |  |  | Third party tax registration number. Used for expense reports |  | Active
MERCHANT_TAXPAYER_ID | VARCHAR2 | 80 |  |  | Third party tax identification number. Used for expense reports |  | Active
COUNTRY_OF_SUPPLY | VARCHAR2 | 5 |  |  | Country where services or goods were originated. Used for expense reports |  | Active
CREDIT_CARD_TRX_ID | NUMBER |  | 18 |  | Credit card transaction identifier |  | Active
COMPANY_PREPAID_INVOICE_ID | NUMBER |  | 18 |  | Invoice ID when this line is a prepaid credit card transaction |  | Active
CC_REVERSAL_FLAG | VARCHAR2 | 1 |  |  | Invoice ID when this line is a prepaid credit card transaction |  | Active
CREATION_DATE | TIMESTAMP |  |  | Yes | Who column: indicates the date and time of the creation of the row. |  | Active
CREATED_BY | VARCHAR2 | 64 |  | Yes | Who column: indicates the user who created the row. |  | Active
LAST_UPDATED_BY | VARCHAR2 | 64 |  | Yes | Who column: indicates the user who last updated the row. |  | Active
LAST_UPDATE_DATE | TIMESTAMP |  |  | Yes | Who column: indicates the date and time of the last update of the row. |  | Active
LAST_UPDATE_LOGIN | VARCHAR2 | 32 |  |  | Who column: indicates the session login associated to the user who last updated the row. |  | Active
PROGRAM_APPLICATION_ID | NUMBER |  | 18 |  | Who column: indicates the application identifier of the row. |  | Active
PROGRAM_ID | NUMBER |  | 18 |  | Who column: indicates the identifier of the row. |  | Active
PROGRAM_UPDATE_DATE | DATE |  |  |  | Who column: indicates the date and time of the creation of the row. |  | Active
REQUEST_ID | NUMBER |  | 18 |  | Enterprise Service Scheduler: indicates the request ID of the job that created or last updated the row. |  | Active
ATTRIBUTE_CATEGORY | VARCHAR2 | 150 |  |  | Descriptive Flexfield: structure definition of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE1 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE2 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE3 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE4 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE5 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE6 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE7 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE8 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE9 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE10 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE11 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE12 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE13 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE14 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
ATTRIBUTE15 | VARCHAR2 | 150 |  |  | Descriptive Flexfield: segment of the user descriptive flexfield. | Invoice Lines (AP_INVOICE_LINES) | Active
GLOBAL_ATTRIBUTE_CATEGORY | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: structure definition of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE1 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE2 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE3 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE4 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE5 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE6 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE7 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE8 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE9 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE10 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE11 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE12 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE13 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE14 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE15 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE16 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE17 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE18 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE19 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
GLOBAL_ATTRIBUTE20 | VARCHAR2 | 150 |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield. |  | Active
LINE_SELECTED_FOR_APPL_FLAG | VARCHAR2 | 1 |  |  | A value of Y indicates that this line on the prepayment invoice is selected for prepayment application |  | Active
PREPAY_APPL_REQUEST_ID | NUMBER |  | 18 |  | Request identifier of the Payables Open Interface Import program that selected this line on the prepayment invoice for prepayment application |  | Active
APPLICATION_ID | NUMBER |  | 18 |  | Unique identifier that identifies the application from where the invoice originated. |  | Active
PRODUCT_TABLE | VARCHAR2 | 30 |  |  | Name of the product source table used for generating an invoice line. |  | Active
REFERENCE_KEY1 | VARCHAR2 | 150 |  |  | Primary key information that will uniquely identify a record in other products view |  | Active
REFERENCE_KEY2 | VARCHAR2 | 150 |  |  | Primary key information that will uniquely identify a record in other products view |  | Active
REFERENCE_KEY3 | VARCHAR2 | 150 |  |  | Primary key information that will uniquely identify a record in other products view |  | Active
REFERENCE_KEY4 | VARCHAR2 | 150 |  |  | Primary key information that will uniquely identify a record in other products view |  | Active
REFERENCE_KEY5 | VARCHAR2 | 150 |  |  | Primary key information that will uniquely identify a record in other products view |  | Active
PURCHASING_CATEGORY_ID | NUMBER |  | 18 |  | Item category unique identifier |  | Active
COST_FACTOR_ID | NUMBER |  | 18 |  | Identifier of the cost component class. Cost Component Classes are used to identify the individual buckets or component costs that make up the total cost of an item, for example, direct material costs, freight costs, labor costs, production or conversion costs and so on. |  | Active
CONTROL_AMOUNT | NUMBER |  |  |  | Optional, user-enterable value to ensure that the calculated tax will be the same as on the physical document. |  | Active
ASSESSABLE_VALUE | NUMBER |  |  |  | User-enterable amount to be used as taxable basis. |  | Active
TOTAL_REC_TAX_AMOUNT | NUMBER |  |  |  | Total recoverable tax allocated to this taxable line. |  | Active
TOTAL_NREC_TAX_AMOUNT | NUMBER |  |  |  | Total non-recoverable tax allocated to this taxable line. |  | Active
TOTAL_REC_TAX_AMT_FUNCL_CURR | NUMBER |  |  |  | Total recoverable tax amount in functional currency. |  | Active
TOTAL_NREC_TAX_AMT_FUNCL_CURR | NUMBER |  |  |  | Total non recoverable tax amount in functional currency. |  | Active
INCLUDED_TAX_AMOUNT | NUMBER |  |  |  | Included tax amount for taxable line of type inclusive. |  | Active
PRIMARY_INTENDED_USE | VARCHAR2 | 30 |  |  | Tax Driver: The purpose for which a product may be used. The actual use will be stored at the distribution level. |  | Active
INTENDED_USE_CLASSIF_ID | NUMBER |  | 18 |  | Tax Driver: Intended use identifier
TAX_ALREADY_CALCULATED_FLAG | VARCHAR2 | 1 |  |  | Internal processing flag for Payables, indicating whether tax has already been calculated. |  | Active
SHIP_TO_LOCATION_ID | NUMBER |  | 18 |  | Tax Driver: Ship to location ID. Value entered by user only if line is not PO matched. |  | Active
PRODUCT_TYPE | VARCHAR2 | 240 |  |  | Tax Driver: Type of product. Possible values are: Goods, Service. This value will default from Inventory Item attributes. Otherwise, value will be entered by user. |  | Active
PRODUCT_CATEGORY | VARCHAR2 | 240 |  |  | Identifies the taxable nature of a noninventory based item for tax determination or tax reporting. |  | Active
PRODUCT_FISC_CLASSIFICATION | VARCHAR2 | 240 |  |  | Tax Driver: Product fiscal classification |  | Active
PROD_FC_CATEG_ID | NUMBER |  | 18 |  | Tax Driver: Product fiscal classification identifier
USER_DEFINED_FISC_CLASS | VARCHAR2 | 240 |  |  | Tax Driver: Fiscal Classification. |  | Active
TRX_BUSINESS_CATEGORY | VARCHAR2 | 240 |  |  | Tax Driver: Transactions category assigned by user. |  | Active
SUMMARY_TAX_LINE_ID | NUMBER |  |  |  | Cross reference to E-Business Tax repository. |  | Active
TAX_REGIME_CODE | VARCHAR2 | 30 |  |  | Tax Regime Code: The set of tax rules that determines the treatment of one or more taxes administered by a tax authority. e.g., VAT Regime in Argentina. |  | Active
TAX | VARCHAR2 | 30 |  |  | A classification of a charge imposed by a government through a fiscal or tax authority. |  | Active
TAX_JURISDICTION_CODE | VARCHAR2 | 30 |  |  | Internal ID of the Tax Jurisdiction. |  | Active
TAX_STATUS_CODE | VARCHAR2 | 30 |  |  | Tax status code. e.g., taxable standard rate, zero rated, exempt, non-taxable. |  | Active
TAX_RATE_ID | NUMBER |  | 18 |  | Internal identifier for tax rate effective on the invoice date. |  | Active
TAX_RATE_CODE | VARCHAR2 | 150 |  |  | Tax rate name associated with tax rate identifier. Tax_rate_id is unique while a tax_rate_code may have different tax rates based on date ranges. |  | Active
TAX_RATE | NUMBER |  |  |  | The rate specified for a tax status in effect for a period of time. |  | Active
TAX_CODE_ID | NUMBER |  | 18 |  | Identifier for existing tax code in Payables. Necessary for upgrade and reporting purposes. |  | Active
HISTORICAL_FLAG | VARCHAR2 | 1 |  |  | Flag to represents whether the document / invoice has been upgraded from a prior release or whether it has been newly created. |  | Active
TAX_CLASSIFICATION_CODE | VARCHAR2 | 30 |  |  | Tax classification code used by Procure To Pay products. |  | Active
SOURCE_APPLICATION_ID | NUMBER |  |  |  | Source document application identifier. |  | Active
SOURCE_EVENT_CLASS_CODE | VARCHAR2 | 30 |  |  | Source document event class code. |  | Active
SOURCE_ENTITY_CODE | VARCHAR2 | 30 |  |  | Entity code of the source document. |  | Active
SOURCE_TRX_ID | NUMBER |  |  |  | Source document transaction identifier. |  | Active
SOURCE_LINE_ID | NUMBER |  |  |  | Source document transaction line identifier. |  | Active
SOURCE_TRX_LEVEL_TYPE | VARCHAR2 | 30 |  |  | Column to record the level at which the source document line identifier is stored. Possible values are LINE, SHIPMENT and FREIGHT. |  | Active
RETAINED_AMOUNT | NUMBER |  |  |  | Retained amount |  | Active
RETAINED_AMOUNT_REMAINING | NUMBER |  |  |  | Retained amount available for release |  | Active
RETAINED_INVOICE_ID | NUMBER |  | 18 |  | Retained invoice identifier. |  | Active
RETAINED_LINE_NUMBER | NUMBER |  |  |  | Retained invoice line number |  | Active
LINE_SELECTED_FOR_RELEASE_FLAG | VARCHAR2 | 1 |  |  | Flag to indicate invoice is currently being processed for release. |  | Active
LINE_OWNER_ROLE | VARCHAR2 | 320 |  |  | This column contains the owner of invoice line derived by AME rule. |  | Active
DISPUTABLE_FLAG | VARCHAR2 | 1 |  |  | Indicates whether the line is disputable |  | Active
RCV_SHIPMENT_LINE_ID | NUMBER |  | 18 |  | Receipt Shipment line unique identifier.Used for Receipt matching. |  | Active
PJC_CONTEXT_CATEGORY | VARCHAR2 | 40 |  |  | Segment used to identify the descriptive flexfield application context for project related standardized code collection | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_PROJECT_ID | NUMBER |  | 18 |  | Identifier of the project used to build the transaction descriptive flexfield for project related transaction distributions | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_TASK_ID | NUMBER |  | 18 |  | Identifier of the task used to build the transaction descriptive flexfield for project related transaction distributions | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_EXPENDITURE_TYPE_ID | NUMBER |  | 18 |  | Identifier of the expenditure used to build the transaction descriptive flexfield for project related transaction distributions | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_EXPENDITURE_ITEM_DATE | DATE |  |  |  | Date on which a project related transaction is incurred | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_ORGANIZATION_ID | NUMBER |  | 18 |  | Organization identifier used to build the transaction descriptive flexfield for project related transaction distributions | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_BILLABLE_FLAG | VARCHAR2 | 1 |  |  | Flag that indicates if a project related item is available to be billed to customers | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_CAPITALIZABLE_FLAG | VARCHAR2 | 1 |  |  | Flag that indicates if a project related item is eligible for capitalization | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_WORK_TYPE_ID | NUMBER |  | 18 |  | Identifier for project related classification of the worked performed | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_CONTRACT_ID | NUMBER |  | 18 |  | Contract Identified.Used when Oracle Contract Billing or Oracle Grants Accounting is installed |  | Active
PJC_CONTRACT_LINE_ID | NUMBER |  | 18 |  | Tracks contract line information. Used when Oracle Contract Billing or Oracle Grants Accounting is installed |  | Active
PJC_FUNDING_ALLOCATION_ID | NUMBER |  | 18 |  | Specifies the name of the project funding override |  | Active
PJC_RESERVED_ATTRIBUTE1 | VARCHAR2 | 150 |  |  | Reserved for future project-related functionality | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_RESERVED_ATTRIBUTE2 | VARCHAR2 | 150 |  |  | Reserved for future project-related functionality | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_RESERVED_ATTRIBUTE3 | VARCHAR2 | 150 |  |  | Reserved for future project-related functionality | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_RESERVED_ATTRIBUTE4 | VARCHAR2 | 150 |  |  | Reserved for future project-related functionality | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_RESERVED_ATTRIBUTE5 | VARCHAR2 | 150 |  |  | Reserved for future project-related functionality | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_RESERVED_ATTRIBUTE6 | VARCHAR2 | 150 |  |  | Reserved for future project-related functionality | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_RESERVED_ATTRIBUTE7 | VARCHAR2 | 150 |  |  | Reserved for future project-related functionality | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_RESERVED_ATTRIBUTE8 | VARCHAR2 | 150 |  |  | Reserved for future project-related functionality | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_RESERVED_ATTRIBUTE9 | VARCHAR2 | 150 |  |  | Reserved for future project-related functionality | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_RESERVED_ATTRIBUTE10 | VARCHAR2 | 150 |  |  | Reserved for future project-related functionality | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_USER_DEF_ATTRIBUTE1 | VARCHAR2 | 150 |  |  | Reserved for user definable project information | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_USER_DEF_ATTRIBUTE2 | VARCHAR2 | 150 |  |  | Reserved for user definable project information | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_USER_DEF_ATTRIBUTE3 | VARCHAR2 | 150 |  |  | Reserved for user definable project information | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_USER_DEF_ATTRIBUTE4 | VARCHAR2 | 150 |  |  | Reserved for user definable project information | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_USER_DEF_ATTRIBUTE5 | VARCHAR2 | 150 |  |  | Reserved for user definable project information | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_USER_DEF_ATTRIBUTE6 | VARCHAR2 | 150 |  |  | Reserved for user definable project information | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_USER_DEF_ATTRIBUTE7 | VARCHAR2 | 150 |  |  | Reserved for user definable project information | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_USER_DEF_ATTRIBUTE8 | VARCHAR2 | 150 |  |  | Reserved for user definable project information | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_USER_DEF_ATTRIBUTE9 | VARCHAR2 | 150 |  |  | Reserved for user definable project information | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
PJC_USER_DEF_ATTRIBUTE10 | VARCHAR2 | 150 |  |  | Reserved for user definable project information | Project Costing Details (PROJECTS_STD_COST_COLLECTION) | Active
ATTRIBUTE_NUMBER1 | NUMBER |  |  |  | Descriptive Flexfield: segment of the user descriptive flexfield.
ATTRIBUTE_NUMBER2 | NUMBER |  |  |  | Descriptive Flexfield: segment of the user descriptive flexfield.
ATTRIBUTE_NUMBER3 | NUMBER |  |  |  | Descriptive Flexfield: segment of the user descriptive flexfield.
ATTRIBUTE_NUMBER4 | NUMBER |  |  |  | Descriptive Flexfield: segment of the user descriptive flexfield.
ATTRIBUTE_NUMBER5 | NUMBER |  |  |  | Descriptive Flexfield: segment of the user descriptive flexfield.
ATTRIBUTE_DATE1 | DATE |  |  |  | Descriptive Flexfield: segment of the user descriptive flexfield.
ATTRIBUTE_DATE2 | DATE |  |  |  | Descriptive Flexfield: segment of the user descriptive flexfield.
ATTRIBUTE_DATE3 | DATE |  |  |  | Descriptive Flexfield: segment of the user descriptive flexfield.
ATTRIBUTE_DATE4 | DATE |  |  |  | Descriptive Flexfield: segment of the user descriptive flexfield.
ATTRIBUTE_DATE5 | DATE |  |  |  | Descriptive Flexfield: segment of the user descriptive flexfield.
GLOBAL_ATTRIBUTE_NUMBER1 | NUMBER |  |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield.
GLOBAL_ATTRIBUTE_NUMBER2 | NUMBER |  |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield.
GLOBAL_ATTRIBUTE_NUMBER3 | NUMBER |  |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield.
GLOBAL_ATTRIBUTE_NUMBER4 | NUMBER |  |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield.
GLOBAL_ATTRIBUTE_NUMBER5 | NUMBER |  |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield.
GLOBAL_ATTRIBUTE_DATE1 | DATE |  |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield.
GLOBAL_ATTRIBUTE_DATE2 | DATE |  |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield.
GLOBAL_ATTRIBUTE_DATE3 | DATE |  |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield.
GLOBAL_ATTRIBUTE_DATE4 | DATE |  |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield.
GLOBAL_ATTRIBUTE_DATE5 | DATE |  |  |  | Global Descriptive Flexfield: segment of the global descriptive flexfield.
OBJECT_VERSION_NUMBER | NUMBER |  | 9 | Yes | Used to implement optimistic locking. This number is incremented every time that the row is updated. The number is compared at the start and end of a transaction to detect whether another session has updated the row since it was queried. |  | Active
JOB_DEFINITION_NAME | VARCHAR2 | 100 |  |  | Enterprise Service Scheduler: indicates the name of the job that created or last updated the row.
JOB_DEFINITION_PACKAGE | VARCHAR2 | 900 |  |  | Enterprise Service Scheduler: indicates the package name of the job that created or last updated the row.
BUDGET_DATE | DATE |  |  |  | Budgetary Calendar Period Date applicable for funds check
FUNDS_STATUS | VARCHAR2 | 30 |  |  | Funds status for an invoice line.
LCM_ENABLED_FLAG | VARCHAR2 | 1 |  |  | Indicates whether invoice line is enabled for landed cost management.
CONSUMPTION_ADVICE_HEADER_ID | NUMBER |  | 18 |  | Consumption advice header identifier. Used for consumption advice matching.
CONSUMPTION_ADVICE_LINE_ID | NUMBER |  | 18 |  | Consumption advice line identifier. Used for consumption advice matching.
SHIP_FROM_LOCATION_ID | NUMBER |  | 18 |  | Ship-from location identifier.
FINAL_DISCHARGE_LOCATION_ID | NUMBER |  | 18 |  | Final discharge location identifier.
FOS_XFACE_FLAG | VARCHAR2 | 1 |  |  | Indicates whether the invoice line information has been interfaced to Supply Chain Financial Flow Orchestration.
MATCHING_RULE_SET_ID | NUMBER |  | 18 |  | Matching rule set identifier of the associated matching rule that was used to update matching information for the invoice line.
MATCHING_RULE_ID | NUMBER |  | 18 |  | Matching rule identifier that was used to update matching information for the invoice line.
FISCAL_CHARGE_TYPE | VARCHAR2 | 30 |  |  | Tax driver. Subclassification for invoice line type of Freight or Miscellaneous. Valid values are from lookup ZX_CHARGE_TYPE.
SHIP_TO_CUST_LOCATION_ID | NUMBER |  | 18 |  | Location where the supplier should ship the goods.
DEF_ACCTG_ACCRUAL_CCID | NUMBER |  | 18 |  | Accrual account that is initially debited for deferred expenses
TRANSACTION_LINE_GEOGRAPHY_ID | NUMBER |  | 18 |  | Tax driver: Expenses location identifier used for tax calculation for payment requests.
Foreign Keys
Table | Foreign Table | Foreign Key Column
AP_INVOICE_LINES_ALL | ap_invoices_all | INVOICE_ID
AP_INVOICE_LINES_ALL | ap_invoices_all | CORRECTED_INV_ID
AP_INVOICE_LINES_ALL | ap_invoice_lines_all | CORRECTED_INV_ID, CORRECTED_LINE_NUMBER
AP_INVOICE_LINES_ALL | po_headers_all | PO_HEADER_ID
AP_INVOICE_LINES_ALL | po_line_locations_all | PO_LINE_ID
AP_INVOICE_LINES_ALL | po_distributions_all | PO_DISTRIBUTION_ID
AP_INVOICE_LINES_ALL | rcv_transactions | RCV_TRANSACTION_ID
AP_INVOICE_LINES_ALL | fa_categories_b | ASSET_CATEGORY_ID
AP_INVOICE_LINES_ALL | pjf_projects_all_b | PJC_PROJECT_ID
AP_INVOICE_LINES_ALL | po_line_locations_all | PO_LINE_LOCATION_ID
AP_INVOICE_LINES_ALL | ap_invoices_all | PA_CC_AR_INVOICE_ID
AP_INVOICE_LINES_ALL | ap_invoice_lines_all | PA_CC_AR_INVOICE_ID, PA_CC_AR_INVOICE_LINE_NUM
AP_INVOICE_LINES_ALL | ap_awt_groups | AWT_GROUP_ID
AP_INVOICE_LINES_ALL | ap_awt_tax_rates_all | TAX_RATE_ID
AP_INVOICE_LINES_ALL | ap_invoices_all | RETAINED_INVOICE_ID
AP_INVOICE_LINES_ALL | egp_system_items_b | INVENTORY_ITEM_ID, ORG_ID
AP_INVOICE_LINES_ALL | ap_invoice_lines_all | RETAINED_INVOICE_ID, RETAINED_LINE_NUMBER
AP_INVOICE_LINES_ALL | ap_distribution_sets_all | DISTRIBUTION_SET_ID
AP_INVOICE_LINES_ALL | gl_ledgers | SET_OF_BOOKS_ID
AP_INVOICE_LINES_ALL | rcv_shipment_lines | RCV_SHIPMENT_LINE_ID
AP_INVOICE_LINES_ALL | gl_ussgl_transaction_codes | SET_OF_BOOKS_ID, USSGL_TRANSACTION_CODE
AP_INVOICE_LINES_ALL | ap_invoices_all | PREPAY_INVOICE_ID
AP_INVOICE_LINES_ALL | ap_invoice_lines_all | PREPAY_INVOICE_ID, PREPAY_LINE_NUMBER
fa_asset_invoices | ap_invoice_lines_all | INVOICE_ID, INVOICE_LINE_NUMBER
fa_mass_additions | ap_invoice_lines_all | INVOICE_ID, INVOICE_LINE_NUMBER
ap_invoice_distributions_all | ap_invoice_lines_all | INVOICE_ID, INVOICE_LINE_NUMBER
ap_apinv_approvers | ap_invoice_lines_all | INVOICE_ID, LINE_NUMBER
fa_mc_asset_invoices | ap_invoice_lines_all | INVOICE_ID, INVOICE_LINE_NUMBER
ap_invoice_lines_all | ap_invoice_lines_all | CORRECTED_INV_ID, CORRECTED_LINE_NUMBER
ap_invoice_lines_all | ap_invoice_lines_all | PA_CC_AR_INVOICE_ID, PA_CC_AR_INVOICE_LINE_NUM
ap_invoice_lines_all | ap_invoice_lines_all | RETAINED_INVOICE_ID, RETAINED_LINE_NUMBER
ap_invoice_lines_all | ap_invoice_lines_all | PREPAY_INVOICE_ID, PREPAY_LINE_NUMBER
ap_allocation_rules | ap_invoice_lines_all | INVOICE_ID, CHRG_INVOICE_LINE_NUMBER
ap_prepay_history_all | ap_invoice_lines_all | INVOICE_ID, INVOICE_LINE_NUMBER
ap_prepay_history_all | ap_invoice_lines_all | PREPAY_INVOICE_ID, PREPAY_LINE_NUM
fa_adj_src_lines_t | ap_invoice_lines_all | INVOICE_ID, INVOICE_LINE_NUMBER
Indexes
Index | Uniqueness | Tablespace | Columns | Status
AP_INVOICE_LINES_N1 | Non Unique | FUSION_TS_TX_IDX | ACCOUNTING_DATE | Active
AP_INVOICE_LINES_N10 | Non Unique | FUSION_TS_TX_IDX | LINE_SELECTED_FOR_APPL_FLAG | Active
AP_INVOICE_LINES_N11 | Non Unique | FUSION_TS_TX_DATA | INVOICE_ID | Obsolete
AP_INVOICE_LINES_N12 | Non Unique | FUSION_TS_TX_DATA | LINE_TYPE_LOOKUP_CODE
AP_INVOICE_LINES_N13 | Non Unique | Default | SET_OF_BOOKS_ID, ORG_ID, ACCOUNTING_DATE, AMOUNT, DISCARDED_FLAG
AP_INVOICE_LINES_N14 | Non Unique | Default | INVOICE_ID, SUMMARY_TAX_LINE_ID
AP_INVOICE_LINES_N2 | Non Unique | FUSION_TS_TX_IDX | RCV_TRANSACTION_ID | Active
AP_INVOICE_LINES_N3 | Non Unique | FUSION_TS_TX_IDX | PO_LINE_LOCATION_ID | Active
AP_INVOICE_LINES_N4 | Non Unique | FUSION_TS_TX_IDX | PJC_PROJECT_ID, PJC_TASK_ID | Active
AP_INVOICE_LINES_N5 | Non Unique | FUSION_TS_TX_IDX | AWARD_ID | Obsolete
AP_INVOICE_LINES_N6 | Non Unique | FUSION_TS_TX_IDX | CORRECTED_INV_ID | Active
AP_INVOICE_LINES_N7 | Non Unique | FUSION_TS_TX_IDX | PREPAY_INVOICE_ID | Obsolete
AP_INVOICE_LINES_N8 | Non Unique | FUSION_TS_TX_IDX | PREPAY_INVOICE_ID, PREPAY_LINE_NUMBER | Active
AP_INVOICE_LINES_N9 | Non Unique | FUSION_TS_TX_IDX | PO_HEADER_ID | Active
AP_INVOICE_LINES_U1 | Unique | FUSION_TS_TX_IDX | INVOICE_ID, LINE_NUMBER | Active
Previous
Next
© Oracle
About Oracle